## Sheet1
Audit App Todo Checklist
	Job	Complete %	Notes
Front-end		69	Makes RESTfull calls to Backend, which processes request and replies with a JSON string which can be used by the front end
Install Dependencies		100
	AngularJS	100	Needed for one page app abilities
	Foundation for Apps	100	Pretty CSS Front. Saves time not having to build all elements
	Ruby	100	Needed for compiling SASS, minifying JS
	NodeJS	100	Used as a Dev Sever and for downloading backend dependencies (Foundation, Angular, Bower, Gulp)
	Bower	100	Used as a frontend dependencies manager, makes updating versions as simple as “bower update” from CLI
	Gulp	100	Used to compile frontend stuff, helps take care of routing etc
Views		38
	Create main layout	80	One base layout which injects all other pages in the form of partials into its “ui-view”
	Login Page	70	Login form sends data and is processed by the backend but Frontend doesnt yet store Auth data
	Dashboard	50	Currently created but lacks functionality
	Audit Create	99	Fully functional form, post's JSON to backend but backend doesn't do anything with it yet.
	Audit Read	10	Currently created but lacks functionality
	Audit Index	80	Fully functional except for pagination
	Audit Update	99	Fully functional form, post's JSON to backend but backend doesn't do anything with it yet.
	About App	10	Currently created but lacks functionality
	Help	10	Currently created but lacks functionality
	Settings	10	Currently created but lacks functionality
	Profile	10	Currently created but lacks functionality
	User Create	0	Currently created but lacks functionality
	User Read	0	Currently created but lacks functionality
	User Index	0	Currently created but lacks functionality
	User Update	0	Currently created but lacks functionality
Controllers		70
	SessionController	100	Set's session on successful login, stored for 1 day. Currently contains Login name, secret token and client number
	DataSender	99	Created but questionable whether further work will be needed. Will only be 100% when whole app complete
	DataReceiver	99	Created but questionable whether further work will be needed. Will only be 100% when whole app complete
	AuthenticationController	50	Send's login form details to back end, should receive either a yes or no back in JSON also containing AuthToken, Username, Client Number and then use AuthenticationController to set the session.
	AuditController	70	CRUD Actions for Audits
	UserController	0	CRUD Actions for Audit Users

Back-end		49
Controllers		67
	Core Controllers	99
	FrontController	100	index.php, Splits url into Controller/Action/Params
	Router	100
	SecurityController	50
	UserController	0
	AuditController	50	Currently holds static data but spits out what is requested and is handled by View/Update frontend working on Database now to store data

Models		30
	Auth Model	80
	User Model	0
	Audit Model	10
Database		50
	Object-relational mapping	99	Have taken NotOrm made it more up to date with Namespaces, modifed to work with our multi-database database and turned it into a vendor file so seperated from the actual MCR (Model Controller Response) back-end. Makes is so we have to write far less MySql and can work in a more Object Oriented way.
	Data structure	50	Started not finished
	Old data migration	0