## Sheet1
Audit App To-do Checklist
	Job	Complete %	Notes
Front-end		66	Makes RESTful calls to Back-end, which processes request and replies with a JSON string which can be used by the front end
Install Dependencies		100
	AngularJS	100	Needed for one page app abilities
	Foundation for Apps	100	Pretty CSS Front. Saves time not having to build all elements
	Ruby	100	Needed for compiling SASS, minifying JS
	NodeJS	100	Used as a Dev Sever and for downloading back-end dependencies (Foundation, Angular, Bower, Gulp)
	Bower	100	Used as a front-end dependencies manager, makes updating versions as simple as “bower update” from CLI
	Gulp	100	Used to compile front-end stuff, helps take care of routing etc
Views		37
	Create main layout	80	One base layout which injects all other pages in the form of partials into its “ui-view”
	Login Page	70	Login form sends data and is processed by the back-end but Front-end doesn't yet store Auth data
	Dashboard	50	Currently created but needs work
	Audit Create	99	Fully functional form, post's JSON to back-end.
	Audit Read	10	Currently created but lacks functionality (Not sure yet if this is needed, might end up being the Audit Take page)
	Audit Index	80	Fully functional except for pagination
	Audit Update	99	Fully functional form, post's JSON to back-end but back-end doesn't do anything with it yet.
	About App	10	Currently created but lacks functionality
	Help	10	Currently created but lacks functionality
	Settings	10	Currently created but lacks functionality
	Profile	10	Currently created but lacks functionality
	Take Audit	99	Currently working on this, needs to be easy to use, simple and fat thumb friendly. This is arguably the most important part of the system so I intend on giving it the most attention.
	Assets Read	0	Currently created but lacks functionality
	Assets Index	0	Currently created but lacks functionality
	User Update	0	Currently created but lacks functionality
	Reports	0	This is the second most important part of the system in my opinion. Plans are written but can't build until the rest of the system is functional so I know what data I have to work with.
	Assign Audit	0	Work in progress
Controllers		63
	Session Controller	100	Set's session on successful login, stored for 1 day. Currently contains Login name, secret token and client number
	Data Sender	99	Created but questionable whether further work will be needed. Will only be 100% when whole app complete
	Data Receiver	99	Created but questionable whether further work will be needed. Will only be 100% when whole app complete
	Authentication Controller	50	Passes login form details to back-end, should receive either a yes or no back in JSON also containing Auth Token, User name, Client Number and then use Authentication Controller to set the session.
	Audit Controller	90	CRUD Actions for Audits – Need to sort Assignments
	User Controller	0	CRUD Actions for Audit Users
	Reports Controller	0
Back-end		61
Controllers		67
	Core Controllers	99
	Front Controller	100	index.php, Splits URL into Controller/Action/Params
	Router	100
	Security Controller	50
	User Controller	0
	Audit Controller	50	Currently holds static data but spits out what is requested and is handled by View/Update front-end working on Database now to store data

Models		55
	Auth Model	80
	Assets Model	0
	Audit Model	85	Audit Read and Create functions made. Need to finish update actions
Database		61
	Object-relational mapping	99	Have taken NotOrm made it more up to date with Name spaces, modified to work with our multi-database database and turned it into a vendor file so separated from the actual MCR (Model Controller Response) back-end. Makes is so we have to write far less MySQL and can work in a more Object Oriented way.
	Data structure	85	Nearly complete just need to build the 'Assets' side of things. Plan in place.
	Old data migration	0
Documentation		78
	Naming Conventions	99
	API Reference Guide	50